## Summary
IT Business Case 2026 | KEYSTONE – Identity & Access Management Rollout
Summary
MCC Country | Corporate |  | Project Manager | Oliver Brandt (IAM Lead)
MCC Decision item ID | 4028 |  | Project Sponsor | Jan-Philipp Weber (CISO)
Project Number(s) | BC-2026-0521.1 |  | Creation date | 2026-09-01
Project Name | KEYSTONE – Identity & Access Management Rollout |  | Start (FY) | 2026
Program Name | VELTRAX Corporate Services GmbH – Group IT Security |  | Go-Live (FY) | 2027
Confidentiality | internal |  | Currency | EUR
Fiscal year | 2026 | 2027 | 2028 | 2029 | 2030 | 2031 | 2032 | 2033 | 2034 | 2035 | Total
I. Cost-Benefit Comparison
Non-capitalizable effort | 170000 | 320000 | 320000 | 320000 | 320000 | 320000 | 320000 | 320000 | 320000 | 320000
Depreciation | 76000 | 136800 | 136800 | 136800 | 136800 | 136800 | 0 | 0 | 0 | 0
Costs
Sales benefits | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Cost savings | 0 | 190000 | 380000 | 380000 | 380000 | 380000 | 380000 | 380000 | 380000 | 380000
Benefits
EBIT - Earnings Before Interest and Taxes
II. Key Figures
Total costs (all years) | 3810000
Total benefits (all years) | 3230000
EBIT (all years) | -580000
Discounted EVA cumulated (all years) | -514442
ROI (all years) | -15%
Payback Period (months) | n/a
Tax Rate | 26.94%
WACC | 5.81%

## Discounted EVA
II. Discounted EVA
Fiscal year | 2026 | 2027 | 2028 | 2029 | 2030 | 2031 | 2032 | 2033 | 2034 | 2035 | Total
EBIT - Earnings before Interest and Taxes | -246000 | -266800 | -76800 | -76800 | -76800 | -76800 | 60000 | 60000 | 60000 | 60000
Calculated Tax | 66269 | 71872 | 20689 | 20689 | 20689 | 20689 | -16163 | -16163 | -16163 | -16163
NOPAT - Net operating profit after taxes | -179731 | -194928 | -56111 | -56111 | -56111 | -56111 | 43837 | 43837 | 43837 | 43837
Capital Employed (residual book value) | 684000 | 547200 | 410400 | 273600 | 136800 | 0 | 0 | 0 | 0 | 0
Calculation Cost of Capital | -39743 | -31795 | -23846 | -15897 | -7949 | 0 | 0 | 0 | 0 | 0
EVA per period | -219474 | -226722 | -79957 | -72008 | -64060 | -56111 | 43837 | 43837 | 43837 | 43837
Discounted EVA per period | -207422 | -202506 | -67495 | -57447 | -48300 | -39983 | 29522 | 27900 | 26368 | 24920
Discounted EVA cumulated | -207422 | -409928 | -477423 | -534870 | -583170 | -623153 | -593631 | -565731 | -539363 | -514442
Basic data for EVA Calculation
Tax Rate: | 26.94% |  | WACC: | 5.81%

## Upload
# | Fiscal year | Type of Cash Out | Short Description | 2026 | 2027 | 2028 | 2029 | 2030 | 2031 | 2032 | 2033 | 2034 | 2035
1 | SC 70 - Project Capitalizable (intern) | One-Off | Internal product, process and architecture effort | 210000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2 | SC 70 - Project Capitalizable (extern) | One-Off | External development / implementation | 390000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 | SC 90 - Software Licenses (intern) | One-Off | Software licences / tooling | 120000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | Local IT/IM Investments (extern) | One-Off | Local rollout infrastructure, hardware and devices | 40000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | SC 10 - Project Non Capitalizable (intern) | One-Off | Internal rollout, testing and change effort | 80000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | SC 10 - Project Non Capitalizable (extern) | One-Off | External rollout, migration and launch support | 90000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | SC 30 - Maint. and Support (intern) | Recurrent | Internal support and application operations | 0 | 60000 | 60000 | 60000 | 60000 | 60000 | 60000 | 60000 | 60000 | 60000
8 | SC 30 - SaaS (extern) | Recurrent | SaaS / cloud services | 0 | 240000 | 240000 | 240000 | 240000 | 240000 | 240000 | 240000 | 240000 | 240000
9 | SC 30 - Maint. for ext. SW Licenses (extern) | Recurrent | External maintenance and vendor support | 0 | 20000 | 20000 | 20000 | 20000 | 20000 | 20000 | 20000 | 20000 | 20000
20 | Cost Savings |  | Wegfall manueller Berechtigungsanträge und Rezertifizierung | 0 | 95000 | 190000 | 190000 | 190000 | 190000 | 190000 | 190000 | 190000 | 190000
21 | Cost Savings |  | Reduzierte Lizenzkosten durch saubere Deprovisionierung | 0 | 70000 | 140000 | 140000 | 140000 | 140000 | 140000 | 140000 | 140000 | 140000
22 | Cost Savings |  | Reduzierter Audit-Aufwand | 0 | 25000 | 50000 | 50000 | 50000 | 50000 | 50000 | 50000 | 50000 | 50000
26 | Non-quantitative Benefits |  | Audit-Sicherheit; Reduktion Angriffsfläche; schnelleres Onboarding.
31 | Project Number |  | BC-2026-0521.1
32 | Start FY |  | 2026
33 | Go-Live FY |  | 2027

## Project Description
Project Name | KEYSTONE – Identity & Access Management Rollout
Project Number | BC-2026-0521.1
Partner / Operating | VELTRAX Corporate Services GmbH
Requesting Unit | Group IT Security
Project Sponsor | Jan-Philipp Weber (CISO)
Project Manager | Oliver Brandt (IAM Lead)
Lead - Affected Countries | CORP; DE; AT; CH; FR; ES; IT; NL; BE; PL; CZ; HU; RO; TR
Description | Konzernweite Einführung eines zentralen IAM (Joiner-Mover-Leaver, Rollenmodell, Rezertifizierung, SSO/MFA) für alle Sparten. Ablösung von 11 lokalen Benutzerverwaltungen und manuellen Berechtigungsanträgen per E-Mail.
Objective (OKR/VCP) | OBJ-311 – Zero-Trust-Grundlage: jede Identität zentral verwaltet.
Metrics | Automatisierte Deprovisionierung innerhalb von 24 h bei Austritt: 100 %; Rezertifizierung aller privilegierten Konten halbjährlich; SSO-Abdeckung 90 % der Kernanwendungen
Planned Deliverables | Rollenmodell je Sparte; Anbindung AD, SAP, M365, Salesforce, WMS; Rollout in 3 Wellen (DACH, West, CEE)
Business Processes affected | Joiner-Mover-Leaver, Berechtigungsvergabe, Rezertifizierung, Audit (SOX-nah).
Organisational Units affected | IT Security, HR (Quelle für Identitäten), Landes-IT, Interne Revision.
Technical Dependencies | HR-Datenqualität (PULSE/SAP HCM) als führendes System; SCIM-Fähigkeit der Zielsysteme.
Organisational Dependencies | Rollenmodell benötigt Fachbereichs-Owner; Betriebsrat DE/AT.
Risks | Rollenmodell wird zu granular und nicht wartbar; Verzögerung durch fehlende HR-Daten für externe Mitarbeiter; Widerstand der Landes-IT
Justification | Revisionsfeststellung 2025: 1.200 verwaiste Konten. IAM ist Prüfungsvorgabe des Wirtschaftsprüfers und Grundlage für SOC (BEACON) und Cloud (SUMMIT).
Vendor / Product Information | SailPoint Identity Security Cloud (Ausschreibungssieger), Entra ID für SSO/MFA.
Hinweis | Fiktives Beispiel für Testzwecke. Alle Firmen-, Personen- und Produktbezüge sind erfunden.